## 📊 Template
User Story Mapping & Journey Board
Map user journeys with stories organized by activity & release
Feature | Theme | RICE Score | Reach | Impact(1-5) | Confidence(%) | Effort(Wks) | Quarter | Status | Dependencies | Owner | Notes
User Dashboard v2 | Core |  | 12000 | 5 | 80 | 8 | 2025-Q3 | In Progress | Auth system | PM
API Rate Limiting | Infrastructure |  | 8500 | 4 | 70 | 6 | 2025-Q3 | In Progress |  | Engineering
Dark Mode Support | UX |  | 5000 | 3 | 90 | 4 | 2025-Q4 | Planned |  | Design
SSO Integration | Enterprise |  | 15000 | 4 | 60 | 10 | 2025-Q4 | Planned | Auth system | Engineering
Export to CSV | Feature |  | 3000 | 2 | 95 | 2 | 2025-Q3 | In Progress |  | Engineering
Onboarding Wizard | Growth |  | 10000 | 5 | 75 | 8 | 2025-Q3 | In Progress |  | PM
Performance Optimization | Infrastructure |  | 8000 | 3 | 70 | 6 | 2025-Q4 | Planned |  | Engineering
📊 OVERVIEW
Total Items |  |  |  | In Progress |  |  |  | Completed

## 📖 Instructions
How to Use: User Story Mapping & Journey Board
Overview
Professional user story mapping & journey board to build better products with structured product management.
Plan
• Define features and initiatives with clear scope
• Score and prioritize using RICE or similar framework
• Set quarterly themes and roadmap timelines
Execute
• Track development progress and dependencies
• Monitor status and remove blockers
• Review metrics and impact post-launch
Pro Tips
💡 Focus on outcomes, not output — measure impact, not velocity
💡 Say no to good ideas to make room for great ones
💡 Involve engineering early in the prioritization process
Key Formulas Used
= RICE = Reach × Impact × Confidence / Effort
= COUNTIF for status tracking
= SUM for effort estimation

## ℹ️ About
About: User Story Mapping & Journey Board
Template Name: | User Story Mapping & Journey Board
Category: | Product Management
Version: | 2.0 Professional
Last Updated: | June 21, 2026
Compatibility: | Excel 2010+, Google Sheets, LibreOffice Calc
License: | MIT - Free for personal & commercial use
Platform: | https://xsheetkit.com
What's Included
• 12 columns with structured data entry
• 7 sample rows with pre-filled data
• Automatic formula calculations
• Data validation dropdowns for consistency
• Conditional formatting for visual insights
Keywords / SEO Tags
user story mapping & journey board,product management,roadmap,features,prioritization,excel template,product development,xsheetkit
(c) 2026 xsheetkit (https://xsheetkit.com) ¦ Original template design by PlanoraNest under MIT License